## Debug
Reference document | Requirement Location | Feature | Sub Feature | Feature Description | Verification Goal | Pass/Fail Criteria | Test Type | Coverage Method | Link to Coverage | Coverage | Notes for test development | Hour estimate | Week 1 | Week 2 | CG | A |  | Notes
RISC-V ISM vol 1 (unpriv. ISA), 20191213 CV32E40P doc rev 46711ac | Section 2.8 Debug chapter | Enter DEBUG mode | EBREAK instruction | Debug mode can be entered by executing the EBREAK or C.EBREAK instruction when dcsr.ebreakm = 1 cause = 1 | Add EBREAK or/and C.EBREAK to arbitrary code Verify that: Core switches into debug mode. Current PC must be saved to DPC Cause of debug must be saved to DCSR (cause=1) PC is updated to value on dm_haltaddr_i input Core starts executing debug cod Ensure exception routine is not enterred | Self Checking Test | Directed Self-Checking | Testcase | Covered in DTC "debug_test" | 100 |  | 1 | 0 |  | OK | Ok
[6 empty] | Check against ISS | Constrained-Random | Functional Coverage
RISC-V ISM vol 1 (unpriv. ISA), 20191213 CV32E40P doc rev 46711ac | Section 2.8 Debug chapter | Enter DEBUG mode | EBREAK instruction | Debug mode can be entered by executing the EBREAK or C.EBREAK instruction when dcsr.ebreakm = 1 cause = 1 | Add EBREAK or/and C.EBREAK to arbitrary exception code Verify that: Core switches into debug mode. PC of EBREAK instruction must be saved to DPC Cause of debug must be saved to DCSR (cause=1) PC is updated to value on dm_haltaddr_i input Core starts executing debug code Ensure exception routine is not entered | Self Checking Test | Directed Self-Checking | Testcase |  | 100 |  | 2 | 0 |  | Difficult to check | Difficult to check | Exceptions are not different from regular code, test not _really_ needed.
[6 empty] | Check against ISS | Constrained-Random | Functional Coverage
RISC-V ISM vol 1 (unpriv. ISA), 20191213 CV32E40P doc rev 46711ac | Section 2.8 Debug chapter | Enter ebreak exception | EBREAK instruction | Enter ebreak exception routine when calling EBREAK or C.EBREAK when dcsr.ebreakm == 0. | Add EBREAK or/and C.EBREAK to arbitrary exception code Verify that: Core switches into debug mode. PC of EBREAK instruction must be saved to DPC Cause of debug must be saved to DCSR (cause=1) PC is updated to value on dm_haltaddr_i input Core starts executing debug code Ensure exception routine is not entered | Self Checking Test | Directed Self-Checking | Testcase | Covered in DTC "debug_test" | 100 |  | 2 | 0 |  | Difficult to check | Difficult to check | Exceptions are not different from regular code, test not _really_ needed.
[6 empty] | Check against ISS | Constrained-Random | Functional Coverage
CV32E40P doc rev 46711ac | Debug chapter | Enter DEBUG mode | External debug event | Debug mode can be entered by asserting the external signal debug_req_i cause is set to = 3 (also see verification goal) | Assert debug_req_i while executing arbitrary code Verify that: Core switches into debug mode. Current PC must be saved to DPC Cause of debug must be saved to DCSR (cause=debugger(0x3)) PC is updated to value on dm_haltaddr_i input Core starts executing debug code | Self Checking Test | Directed Self-Checking | Testcase | Covered in DTC "debug_test" | 100 |  | 0 | 0 |  | OK | OK |  | May need to add more CSR checks
[6 empty] | Check against ISS | Constrained-Random | Functional Coverage
CV32E40P doc rev 46711ac RISCV-V External Debug Support Version 0.13.2 | Debug chapter Chapter 5 | Trigger module | Trigger module match event | The CV32E40P contains a trigger module with a single trigger register capable of triggering on instruction address match. Write '1' to tdata1[2] to enable matching Write breakpoint addr to tdata2 register cause = 2 | Verify that core enters debug mode when the trigger matches on instruction address. NB! According to spec, the tdataN registers can only be written from debug mode, as m-mode writes are ignored. Enter debug mode by any of the above methods. Write (randomized) breakpoint addr to tdata2 and enable breakpoint in tdata1[2] Exit debug mode (dret instruction) Verify that core enters debug mode on breakpoint addr Current PC is saved to DPC Cause of debug must be saved to DCSR (cause=2) PC is updated to value on dm_haltaddr_i input Core starts executing debug code | Self Checking Test | Directed Self-Checking | Testcase | Covered in DTC "debug_test" | 100 |  | 2 | 0 |  | OK | OK
[6 empty] | Check against ISS | Constrained-Random | Functional Coverage
CV32E40P doc rev 46711ac RISCV-V External Debug Support Version 0.13.2 | Debug chapter Chapter 5 | Trigger module | Trigger module match event | When trigger module is disabled, no trigger should fire even though the PC matches the address in tdata2. | Enter debug mode by any of the above methods. Write (randomized) breakpoint addr to tdata2 and disable breakpoint in tdata1[2] Exit debug mode (dret instruction) Verify that core does not enter debug mode on breakpoint addr | Self Checking Test | Directed Self-Checking | Testcase |  | 100 | Reuse of trigger test, add flag to only set match addr but not enable bit. | 2 | 0 |  | OK | OK
[6 empty] | Check against ISS | Constrained-Random | Functional Coverage
CV32E40P doc rev 46711ac | Debug chapter | Debug exception addr |  | If an exception occurs during debug mode, the PC should be set to the dm_exception_addr_i input without changing the status registers | Bring core into debug mode, generate all exception types and observe that the PC jumps to the address given by dm_exception_addr_i. Observe no change in status registers According to specification, the cf32e40p supports the following types of exceptions: Illegal instruction (2) Breakpoint (3) Environment call from M-mode (ECALL) (11) | Self Checking Test | Directed Self-Checking | Testcase | Covered in DTC "debug_test" | 100 | Checks for cause. | 1 | 0 |  | Ok | OK |  | Only one exception tested
[6 empty] | Check against ISS | Constrained-Random | Functional Coverage
CV32E40P doc rev 46711ac | Debug chapter | Core debug registers |  | Accessing the core debug registers - DCSR, DPC and DSCRATCH0/1 while NOT in debug mode causes an illegal instruction | Access all debug registers in M-mode and observe that illegal instruction exception is triggered. | Self Checking Test | Directed Non-Self-Checking | Testcase | Covered in DTC "debug_test" | 100 | Reuse of trigger test, add flag to only set match addr but not enable bit. | 2 | 0 |  | OK | OK
[6 empty] | Check against ISS | Constrained-Random | Functional Coverage
CV32E40P doc rev 46711ac | Debug chapter | Trigger module registers |  | Accessing the trigger module registers - tselect, tdata1/2/3 while NOT in debug mode causes an illegal instruction This has been changed in the CV32E40P specification to be compliant with debug spec. SW can read these trigger CSRs in non-debug mode, but cannot write to these CSRs. Also add in TINFO (this was a reent change) | Access all trigger module registers in M-mode and observe that illegal instruction exception is triggered. Writes to trigger CSRs in non-debug mode are ignored. Reads of trigger CSRs reflect updated values. | Self Checking Test | Directed Self-Checking | Testcase | Covered in DTC "debug_test" | 100 |  |  |  |  | OK | ok- | missing some csr checks
[6 empty] | Check against ISS | Constrained-Random | Functional Coverage
RISC-V External Debug Support Version 0.13.2 | 4.1 Debug mode pt2 | Program Buffer | Interrupts | While in debug mode and executing from the program buffer, all interrupts are masked. | Enable interrupts (setting mstatus.mie field and mie register). Bring core into debug mode and start executing from program buffer. Generate interrupts while in debug mode and ensure they are masked. | Self Checking Test | Directed Self-Checking | Testcase |  | 100 |  | 0 | 0 |  | OK | OK |  | Requires virtual peripheral to generate irq
[6 empty] | Check against ISS | Constrained-Random | Functional Coverage
RISC-V External Debug Support Version 0.13.2 | 4.1 Debug mode pt3 | Program Buffer | Exceptions | While in debug mode and executing from the program buffer, exceptions don’t update any registers but they DO end execution of PB (TBD: goes back to M-mode or restarts in debug(?)) [PZ] this is redundnant with dm_exception_addr_i (on line 10 & 11) | Bring core into debug mode and start executing from program buffer. Make sure PB includes code that will hit an exception. Make sure core doesn’t update any registers, and jumps out of debug mode into M-mode | Self Checking Test | Directed Self-Checking | Testcase |  | 100 |  | 0 | 0 |  | OK | OK | Does not hit all, needs refinement
[6 empty] | Check against ISS | Constrained-Random | Functional Coverage
RISC-V External Debug Support Version 0.13.2 | 4.1 Debug mode pt4 | Program Buffer | Triggers | While in debug mode and executing from the program buffer, no action is taken on any trigger match. | Bring core into debug and enable a trigger on the PC (pointing to the debug program buffer). Continue execution in debug, and observe that no action is taken when the trigger matches. | Self Checking Test | Directed Self-Checking | Testcase |  | 100 |  | 3 |  | 3 | OK | Ok | Only checks one irq line
[6 empty] | Check against ISS | Constrained-Random | Functional Coverage
RISC-V External Debug Support Version 0.13.2 | 4.1 Debug mode pt5 | Program Buffer | Counters | Spec:Counters may be stopped, depending on stopcount in dscr For CV32E40P, stopcount not implemented, counters are not stopped during debug. | N/A for CV32E40P : need Arjan/Davide to sign-off on this. [PZ] We will need a test to ensure counters do not stop couting in debug mode. We cannot disable counters as stopcount is not implemented. | Self Checking Test | Directed Self-Checking | Testcase |  | 100 |  | 4 | 0 |  | OK
[6 empty] | Check against ISS | Constrained-Random | Functional Coverage
RISC-V External Debug Support Version 0.13.2 | 4.1 Debug mode pt6 | Program Buffer | Timers | Timers may be stopped, depending on stoptime in dcsr | N/A for CV32E40P : need Arjan/Davide to sign-off on this. [PZ] I confirm that this is not needed on CV32E40P. There is no timer in CV32E40P.
RISC-V External Debug Support Version 0.13.2 | 4.1 Debug mode pt7 | Program Buffer | WFI instruction | In debug, the WFI instruction acts as a NOP instruction | Bring core into debug mode. Ensure that an WFI instruction will be executed from the program buffer. Ensure that the WFI will act as a nop, not waiting for an interrupt to occur. | Self Checking Test | Directed Self-Checking | Testcase |  | 100 | Insert WFI in debug mode and ensure progress is made without interrupts https://github.com/riscv/riscv-debug-spec/issues/545 |  |  |  | N/A | N/A
[6 empty] | Check against ISS | Constrained-Random | Functional Coverage
RISC-V External Debug Support Version 0.13.2 | 4.1 Debug mode pt8 | Program Buffer | Priv. lvl changes | An ebreak instruction during debug shall result in relaunching the debugger entry code by setting the PC to the halt_addr_i and will not change any CSR in doing this. | Bring hart into debug mode and start executing from the Program Buffer. Make sure the PB code includes an ebreak instruction. When the ebreak is executed, the hart must halt and not update dpc or dcsr. Ensure relaunch of debugger entry | Self Checking Test | Directed Self-Checking | Testcase |  | 100 | Must check mcycle and minstret | 3 | 0 |  | OK | OK
[6 empty] | Check against ISS | Constrained-Random | Functional Coverage
RISC-V External Debug Support Version 0.13.2 | 4.1 Debug mode pt9 | Program Buffer | Fence instructions | Completing program buffer execution is considered output for the purpose of the fence instruction. | TBD - need to understand the fence instruction in cv32e40p. Is "completing program buffer execution" the same as executing dret? [PZ] waiting for more clarity from RISCV Foundation debug task group (see https://lists.riscv.org/g/tech-debug/topic/clarification_request/75725318?p=,,,20,0,0,0::recentpostdate%2Fsticky,,,20,2,0,75725318 ) |  |  | Functional Coverage | [6 empty] | N/A | N/A
RISC-V External Debug Support Version 0.13.2 | 4.1 Debug mode pt10 | Program Buffer | Ctrl. Transfer instr. | All control transfer instructions may act as illegal instructions if destination is within program buffer. If one does, all must. | N/A for CV32E40P : need Arjan/Davide to sign-off on this. [PZ] This is not supported and it is mentioned in the CV32E40P debug spec. No verification needed to prove nor dis-prove this behavior |  |  |  |  | 100 | Insert WFI in debug mode and ensure progress is made without interrupts | 1 | 0 |  | OK | OK
RISC-V External Debug Support Version 0.13.2 | 4.1 Debug mode pt11 | Program Buffer | Ctrl. Transfer instr. | All control transfer instructions may as illegal instructions if destination is outside the program buffer. If one does, all must. | N/A for CV32E40P : need Arjan/Davide to sign-off on this. [PZ] This is not supported and it is mentioned in the CV32E40P debug spec. No verification needed to prove nor dis-prove this behavior
RISC-V External Debug Support Version 0.13.2 | 4.1 Debug mode pt12 | Program Buffer | Instr. Dependent of PC | Instructions that depend on the PC may act as illegal instructions | N/A for CV32E40P : need Arjan/Davide to sign-off on this. [PZ] This is not supported and it is mentioned in the CV32E40P debug spec. No verification needed to prove nor dis-prove this behavior |  |  |  |  | 100 |  | 2 | 0 |  | OK | OK | should check dpc/dcsr
RISC-V External Debug Support Version 0.13.2 | 4.1 Debug mode pt13 | Program Buffer | Effective XLEN | Effective XLEN = DXLEN | CV32E40P XLEN=1 (32 bits). DXLEN is defined as the widest supported XLEN. For now, this will be 1 (32 bits). Check XLEN M- and D-mode Mike: what exactly would a testcase actually do to check this? ØK: As discussed in the meeting 02.July, this is probably a SW/DM problem. Leaving it here for reference.
RISC-V External Debug Support Version 0.13.2 | 4.2 Load-Reserved/Store-Conditional |  |  |  | N/A for CV32E40P (requires A-extention) : need Arjan/Davide to sign-off on this. [PZ] This is not a test but a warning or assumption that debug entry should not occur between a lr and sc instruction pair. Moreover, CV32E40P does not support A-extension
RISC-V External Debug Support Version 0.13.2 | 4.3 Wait for interrupt | Debug mode | WFI instruction | If debug_req_i is asserted while waiting for interrupt (core_sleep_o = 1), WFI instruction must complete (core_sleep_o -> 0) and hart enters debug mode. | Insert WFI instruction into arbitrary code. While the hart is waiting for an interrupt, request debug mode. The hart must stop waiting for interrupt and enter debug mode. WFI at trigger will be converted to a NOP and should be a dedicated test. See #pz_ref2 in this sheet below | Self Checking Test | Directed Self-Checking | Testcase | [9 empty] | Requires a delay in the virtual peripheral to allow core to start execute WFI before debug_req is asserted
[6 empty] | Check against ISS | Constrained-Random | Functional Coverage
RISC-V External Debug Support Version 0.13.2 | 4.4 Single step | Debug mode | Single stepping | By setting step in dcsr[2] before resuming execution, a debugger can cause the hart to execute a single instructin before re-entering debug mode. | Bring the hart into debug mode. Set the step bit in dcsr[2] and then resume execution. Observe that the hart runs a single instruction and the goes back to debug mode. | Self Checking Test | Directed Self-Checking | Testcase | [9 empty] | [PZ[ assertion added in design ccv32e40p_cs_registers.sv
[6 empty] | Check against ISS | Constrained-Random | Functional Coverage
RISC-V External Debug Support Version 0.13.2 | 4.4 Single step | Debug mode | Single stepping | If the instruction being fetched or executed in a single step casues an exception, debug mode is entered immediately after the PC is changed to the exception handler and registers tval and cause are updated. Note: CV32E40P does not support tval (this should be supported in future cores) | Perform a single step. Make sure the instruction executed in the step will cause an exception. PC must jump to the exception handler address and update tval and cause and then immediately enter debug mode. Check tval==0, then on future cores, when implemented, it will fail and require a test update | Self Checking Test | Directed Self-Checking | Testcase
[6 empty] | Check against ISS | Constrained-Random | Functional Coverage |  | 100 |  | 2 | 0 |  | OK | OK
RISC-V External Debug Support Version 0.13.2 | 4.4 Single step | Debug mode | Single stepping | If the instruction being fetched or executed in a single step causes a trigger, debug mode is entered immediately after the trigger fired. Cause is set to 2 instead of 4 | Set up the trigger module to match on instruction address. Set up single stepping such that the match address will be executed in a step. The trigger module must fire during the step, and debug mode entered with cause = 2 to identify that the trigger was fired. (#1) | Self Checking Test | Directed Self-Checking | Testcase
[6 empty] | Check against ISS | Constrained-Random | Functional Coverage |  | 100 | Set up basic infrastructure for single stepping. | 4 | 0 |  | OK | OK | in cs_registers by PaulZ
RISC-V External Debug Support Version 0.13.2 | 4.4 Single step | Debug mode | Single stepping | If the intruction executed in the single step results in a PC that will cause an exception, the exception will not execute until the next time the hart resumes. | Make sure that an instruction in the instruction memory will generate a PC that causes an exception. Set up single stepping and make sure to step through this specific instruction. Hart must go back to debug mode after stepping, and the exception must not start executing until the next time the hart resumes (either single step or exit debug mode) | Self Checking Test | Directed Self-Checking | Testcase
[6 empty] | Check against ISS | Constrained-Random | Functional Coverage |  | 100 | NB. Does not currently check DPC, but program executes as expected. | 2 |  | 0 | OK | OK
RISC-V External Debug Support Version 0.13.2 | 4.4 Single step | Debug mode | Single stepping | If the intruction executed in the single step results in a PC that will cause a trigger event, the trigger event will not take place until the instruction is executed. | This can be verified in the same steps as marked with (#1). Mike: this may be difficult to accurately predict in the ISS. This is good input for the Imperas team. | Self Checking Test | Directed Self-Checking | Testcase
[6 empty] | Check against ISS | Constrained-Random | Functional Coverage |  | 100 |  | 4 |  | 0 | OK | OK
RISC-V External Debug Support Version 0.13.2 | 4.4 Single step | Debug mode | Single stepping | If the single step instruction is WFI, it must be treated as a nop instead of stalling and waiting for interrupt. [PZ] #pz_ref2 | Perform a single step where the instruction to be executed is a WFI instruction. The hart must not wait for interrupt, but treat the instruction as as NOP and re-enter debug after finishing the step. | Self Checking Test | Directed Self-Checking | Testcase
[6 empty] | Check against ISS | Constrained-Random | Functional Coverage |  |  |  | 0 |  | 0 | N/A | N/A
RISC-V External Debug Support Version 0.13.2 | 4.5 Reset | Debug mode | Reset | When the hart comes out of reset, it must immediately enter debug mode without executing any instructions if the halt signal or debug_req_i is asserted. | Assert the core reset AND the debug_req_i signal. The hart must not execute any instructions, but immediately enter debug mode. | Self Checking Test | Directed Self-Checking | Testcase | [6 empty] | N/A | N/A |  | Requires tb to make virtual peripheral assert debug req before releasing reset
[6 empty] | Check against ISS | Constrained-Random | Functional Coverage |  | 100 |  | 0 |  | 0 | OK |  | defer
RISC-V External Debug Support Version 0.13.2 | 4.6 dret instruction | Debug mode | dret instruction | Executing dret while NOT in debug mode will cause an illegal instruction exception. | Insert dret into arbitrary code running in m-mode, observe that the illegal insctruction exception is thrown. Can be tested in the same test as for debug entry | Self Checking Test | Directed Self-Checking | Testcase
[6 empty] | Check against ISS | Constrained-Random | Functional Coverage |  | 100 |  | 1 |  | 0 | OK | OK
RISC-V External Debug Support Version 0.13.2 | 4.6 dret instruction | Debug mode | dret instruction | Executing dret while in debug mode will restore PC to the value in dpc and exit debug mode. (privilege level will be restored to the value in dcsr). Note: CV32E40P only supports machine mode. | Bring hart into debug mode. Execute a dret instruction and observe that the hart resumes executing from the correct address as given by dpc. Can be tested in the same test as for debug entry. | Self Checking Test | Directed Self-Checking | Testcase
[6 empty] | Check against ISS | Constrained-Random | Functional Coverage |  | 75 | UVM agent ready, directed and random tests fail due to uninitialize stack. New test in progress |  |  | 2
RISC-V ISM vol 1 (unpriv. ISA), 20191213 | Section 2.8 Debug chapter | Semihosting |  | To enable semihosting, a special instruction sequence is needed as there is only a single EBREAK instruction available. slli x0, x0, 0x1f # Entry NOP ebreak # Break to debugger srai x0, x0, 7 # NOP encoding the semihosting call number 7 [PZ] This is a software convention and need not be tested in verification. As long as the above instructions work in general, then no need for dedicated semihosting testing. | If all points above passes, there should be nothing to verify here. Semihosting will be handled from SW.
|  | Trigger | Exception handling | If the trigger matches on an illegal instruction, PC must be set to the exception handler prior to entering debug mode. | Set up the trigger to match on an address containing an illegal instruction. When the trigger fires, ensure that cause=0x2(trigger) and that PC is set to the exception handler before entering debug mode. | Self Checking Test |  |  |  |  | https://github.com/riscv/riscv-debug-spec/issues/545 | 1 | 1 |  | N/A | N/A
[6 empty] | Check against ISS | [8 empty] | N/A | N/A
|  | Trigger, single step | Exception handling | If the trigger matches on an illegal instruction, PC must be set to the exception handler prior to entering debug mode. | Set up the trigger to match on an address containing an illegal instruction. Set up single stepping such that the match address will be executed in the next step. When the trigger fires, ensure that cause=0x2(trigger) and that PC is set to the exception handler before entering debug mode. | Self Checking Test |  |  |  |  | https://github.com/riscv/riscv-debug-spec/issues/545 | 2 |  | 2 | N/A | N/A
[6 empty] | Check against ISS | [8 empty] | N/A | N/A
RISC-V External Debug Support Version 0.13.2 CV32E40P doc rev 46711ac | 4.8.1 DCSR Control and Status Registers | Single step | Interrupts | While single stepping, interrupts may be enabled or disabled using the dcsr.stepie bit. | Set up single stepping. Ensure interrupt is asserted while performing a step. Ensure that the interrupt is taken when dcsr.stepie = 1, and not taken when dcsr.stepie = 0. | Self Checking Test | Directed Self-Checking | Testcase |  | 100 |  | 8 |  | 0 | OK
[6 empty] | Check against ISS | Constrained-Random | Functional Coverage
[5 empty] | Have debug_req_i and interrupt asserted on same clock cycle. Ensure debugger entered with PC reflecting normal PC thread (not the interrupt exception address) | Self Checking Test | Directed Self-Checking | Testcase |  | 100 | Must figure out timing on this one. TBD: Test passed, but according to github issue it should fail. Seems like an internal irq signal must be aligned to debug_req_i. | 8 | 0 |  | OK- needs check
[6 empty] | Check against ISS | Constrained-Random | Functional Coverage
|  | RISCV compliance |  | All RISCV code should run in debug mode as well as M mode | Run RISCV compliance tests all in debug | Self Checking Test | Directed Self-Checking | Testcase |  | 0 |  | 16 |  | 16
[5 empty] | [PZ] assert debug_req and interrupt at the same time as trigger is matching an address (with trigger enabled) and the instruction being 1) illegal instruction 2) exception call (e.g. ebreak with ebreakm==0) 3) branch 4) multicycle instruction (e.g. mulh) | [5 empty] | Not sure how to accomplish this in the directed test
[5 empty] | [PZ] Add coverage to ensure debug_req asserted on every FSM state | Check against ISS | Constrained-Random | Functional Coverage | [6 empty] | OK | N/A
[5 empty] | [PZ] Have trigger address match an instruction that has an illegal instruction (both in normal and single step mode). Ensure debug is enterred with cause set to trigger and PC is set to exception handler prior to debug entry |  |  |  |  | 100 |  | 1 | 0 |  | OK | OK
[PZ] Have debug_req_i and interrupt asserted on same clock cycle. Ensure debugger entterred with PC reflecting normal PC thread (not the interrupt exception address)
RISC-V External Debug Support Version 0.13.2 CV32E40P doc rev 46711ac | 4.8.1 DCSR Control and Status Registers | Single Step | stepie | [PZ] 0: Interrupts are disabled during single stepping. 1: Interrupts are enabled during single stepping. | [PZ] During single step, assert interrupt and ensure that interrupt is taken when stepie==1 and not taken when stepie==0 |  |  |  |  | 100 |  | 0 | 0 |  | OK | OK
[5 empty] | [PZ] Setup up trigger to not be enabled (tmatch.execute ==0) and trigger address (tdata2) to match an address that will be executed by the core. Ensure no trigger occurs. |  |  |  | Covered in DTC "debug_test" | [5 empty] | N/A | N/A
[5 empty] | [PZ] Run RISCV compliance tests all in debug mode | [5 empty] | https://github.com/riscv/riscv-debug-spec/issues/545 | 1 | 1 |  | N/A | N/A
[5 empty] | [PZ] Write to TSELECT non-zero value and ensure zero always returned. TINFO read should always reflect match address feature. | [9 empty] | N/A | N/A
[5 empty] | [PZ] assert debug_req and interrupt at the same time as trigger is matching an address (with trigger enabled) and the instruction being 1) illegal instruction 2) exception call (e.g. ebreak with ebreakm==0) 3) branch 4) multicycle instruction (e.g. mulh) | [5 empty] | https://github.com/riscv/riscv-debug-spec/issues/545 | 2 |  | 2 | N/A | N/A
[5 empty] | [PZ] Add coverage to ensure debug_req asserted on every cv32e40p_controller module FSM state | [9 empty] | N/A | N/A
[10 empty] | 100 |  | 8 |  | 0 | OK
[10 empty] | 100 | Must figure out timing on this one. TBD: Test passed, but according to github issue it should fail. Seems like an internal irq signal must be aligned to debug_req_i. | 8 | 0 |  | OK- needs check
[10 empty] | 0 |  | 16 |  | 16
Not sure how to accomplish this in the directed test
[15 empty] | OK | N/A
[12 empty] | 109 | 2 | 41 | 43
-------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------- END -----------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------
Note on E6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is covered in Exceptions Vplan. If it is already covered by debug_test (or related), let's keep with here with an acknowledgement that it is also in Exceptions. Otherwise, we can strike it from this Vplan. Reply: Team decided to keep it here.
Note on E18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is already covered in the CSR Vplan. Suggest we strike it from this Vplan. Reply: Redundant but already here, soo we will leave it.
Note on E20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I like Paul's suggested re-wording.
Note on E22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Strike it? Reply: yes
Note on F28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Strike it? Reply: Done
Note on E31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These two statements seem incompatible... Reply: No privl levels - used PZ wording
Note on F33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Where are we on this? Reply: Boils down to : execute fence instruction while in debug mode.
Note on E34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Strike it? Reply: agreed
Note on E35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Strike it? Reply: Agreed.
Note on E36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Strike it? Reply: Agreed.
Note on E37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Strike it?
Note on E39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Strike it?
Note on G41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Strike the random test? Reply: No, the random test already does that.
Note on F44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Agree with Paul's suggestion (very clever). Reply: Oystein to update test - may already be done.
Note on I49: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Any thoughts on how this would be coded? Reply: Turns out, this is not a testable condition on E40P
Note on E58: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Strike the bit about priv level.
Note on E60: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Agree with Paul. Recommend we strike this Feature from the Vplan.
Note on F77: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Interesting. I will take this one. Not sure of the mechanics, but should be able to figure it out. The extension would be to run any randomly generated test-program in debug mode. Reply: Better idea: cross coverage of debug mode entry and instruction executed
Note on F78: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These are redundant with the CSR Vplan. We can safely stike this from this Vplan. Reply: Already in Directed Debug test. Leave it.
Note on F80: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Which FSM?

## DONOTDELETE
Pass/Fail Criteria | Test Type | Coverage Method
Self Checking Test | RISC-V Compliance | Testcase
Signature Check | OpenHW Compliance | Functional Coverage
Check against ISS | Directed Self-Checking | Assertion Coverage
Check against RM | Directed Non-Self-Checking | Code Coverage
Assertion Check | Constrained-Random
Other | Other

## License Statement
Copyright 202[x] Silicon Labs Inc.
This document, all associated software, and derivatives thereof are licensed under the Solderpad License, Version 2.0 (the "License").
Use of this file means you agree to the terms and conditions of the License and are in full compliance with the License.
You may obtain a copy of the License at:
https://solderpad.org/licenses/SHL-2.0/
Unless required by applicable law or agreed to in writing, software and hardware implementations thereof distributed under the License is distributed on an "AS IS" BASIS, WITHOUT WARRANTIES OR CONDITIONS OF ANY KIND, EITHER EXPRESSED OR IMPLIED.
See the License for the specific language governing permissions and limitations under the License.