## README
Copyright 2020 by the OpenHW Group
Licensed under the Solderpad Hardware License, Version 2.0
Purpose of this Document
This document captures the Functional RTL Freeze criteria for OpenHW Group RTL IP.
RTL IP
For the purposes of this document, RTL IP shall mean designs and associated collateral that can be use to realize a functional design in either an FPGA, ASIC or both. The RTL IP is captured as synthesizable SystemVerilog.
What Does “Functional RTL Freeze” Mean?
In a nutshell, ‘Functional RTL Freeze’ means that the IP is complete, functionally correct, validated against a specific software toolchain and ready to be used in a commercial-grade product. The Specification, Design and Verification are complete and self-consistent. That is, the RTL has been shown to match the design intent as captured in the specification by means of either dynamic or static verification methods (or both).
Deliverables: OpenHW provides the following at RTL Freeze:
- A complete User Manual including implementation guidelines
- RTL source code (licensed under Solderpad 2.0)
- Verification Plans and Reports
- Verification Environment source code
- Software compliance report

## Documentation
Category | Item | Sign-off Criteria | Exceptions/Waivers
Publication | User Manual | Tagged version of source available in core-v-docs
Formally released static version attributed to core-v-docs tag
No open or non-waived issues assigned to tagged release
| Errata | List of waived core-v-docs issues related to tagged release
User Manual Content | CORE Integration | Chapter reviewed and signed-off as a complete.
Completed RISC-V ISA Compliance Review
Each parameter and pin described
|  | Completed RISC-V ISA Compliance Review | Not Applicable
| ISA of CORE-specific instruction extensions | Chapter reviewed and signed-off as a complete.
Completed RISC-V ISA Compliance Review
| Control and Status Registers | Chapter reviewed and signed-off as a complete.
Completed RISC-V ISA Compliance Review
| Performance Counters | Chapter reviewed and signed-off as a complete.
Completed RISC-V ISA Compliance Review
| Exceptions and Interrupts | Chapter reviewed and signed-off as a complete.
Completed RISC-V ISA Compliance Review
| Debug support | Chapter reviewed and signed-off as a complete.
Completed RISC-V ISA Compliance Review
| Trigger support | Chapter reviewed and signed-off as a complete.
Completed RISC-V ISA Compliance Review
| Tracer support | Chapter reviewed and signed-off as a complete.
Completed RISC-V ISA Compliance Review
| Synthesis guidelines | Chapter reviewed and signed-off as a complete.
|  | Completed RISC-V ISA Compliance Review | Not Applicable

## RTL Design
Category | Item | Sign-off Criteria | Exceptions/Waivers
Configuration | Version clearly identified | The version at this release is clearly identified in GitHub and in the RTL freeze review document.
Coding rules | Module and File names | No two modules in the design have the same name. Each module name shall be prefixed with the project name (e.g. cv32e40p_<module>) Each module name shall match the file name using the system verilog suffix ".sv" (e.g. cv32e40p_controller module located in cv32e40p_controller.sv file) Each system verilog file shall contain only one module definition
| Implementation HDL | The design does not mix HDLs.
| Low technology dependence | In IP designs, technology-specific blocks (mainly RAM cells) are accessible and easily replaced by blocks targetting other ASIC or FPGA technologies. | This criterion does not apply to SoC/silicon projects.
| No use of ifdef, ifndef, defines | No ifdef, ifndef or defines used anywhere in RTL | Except for assertions, which shall be within a define using the project name (e.g. <PROJECT_NAME>_ASSERT_ON)
| No unfinished code | No comments in code alluding to potential fixes or changes. Comments include "todo", "tbd", "fixme"
| No open non-waived RTL bugs in github | No open non-waived issues with both label Component:RTL and Type:Bug | Waiving can be done by applying the WAIVED:<PROJECT_NAME>. Issues labeled with a non-applicable parameter option are waived as well in case the RTL Freeze configuration applies to a different parameter configuration
| No dependency on external repositories for design | No dependency on external repositories for design
Design rules | Clock domain crossing | Synchronizers shall be implemented with a component module (similar to clock gate) in order for implementation to replace with 2 or 3 flip-flop synchronizer based on technology and MTBF requirements
| Asynchronous inputs | Asynchronous inputs have an adequate synchronizer(s).
| Synchronous design | Fully synchronous design | Other design styles clearly identified in the code, in the documentation along with synthesis/STA guidelines.
| Synchronous design | No delay line (based on propagation time)
| Synchronous design | No combinational loops
| Multicycle path | No multicycle path | Multicycles necessary, clearly identified in the code, in the documentation along with synthesis/STA guidelines.
| Clock edges | Only one active clock edge in the design | Other clock schemes necessary, clearly identified in the code, in the documentation along with synthesis/STA guidelines.
| Gating clock | Gated clocks necessary, clearly identified in the code, in the documentation along with synthesis/STA guidelines.
| No latch | Latches may be implemented for large memory elements (such as register files) using a parameter to select between register vs latched design
| Reset signal | Only one reset signal in the design | Other design styles necessary, clearly identified in the code, in the documentation along with synthesis/STA guidelines.
| Reset fanout | Same type of reset in the whole design (synchronous/asynchronous, active high/low)
| FSM reset | FSM state register has a reset
| No tri-state | No internal tri-state buffers | Does not apply to I/O pads.
Synthesizable IP | Linting | A linting tool was used; it reports no error and all outstanding warnings can be waived.
Open-source | Third-party audit | Eclipse “CQ” audit complete
| No closed-source | All RTL code in the design is open-source. It includes the appropriate licence notices.
| OpenHW design licence | OpenHW Group RTL source code is under the Solderpad 2.0 licence
| Third-party IP licence | Third party IP licence terms do not contaminate other designs in the modules and do not prevent to use the design in closed-source projects (e.g. GPL IP cannot be integrated in OpenHW projects).
| No export restrictions | Contributions do not include controlled software or technology or other information that is subject to export control laws and regulations in any applicable jurisdictions, including but not limited to U.S. Export Administration Regulations (15 CFR Chapter VII, Subchapter C, Parts 730-744, EAR). [Excerpt from OpenHW Group Membership Agreement] OpenHW members are bound to this agreement; the use of external IP is not.

## Functional Verification
Category | Item | Sign-off Criteria | Exceptions/Waivers
Verification Planning | Top-level Verification Plan | Top-level plan is complete | None allowed
| Per-functional Category Verification Plan | Completed, reviewed and up-issued per review | Captured as core-v-docs issues
| Testbench Cross-reference | Each item in Vplan cross-ref’ed to testcase and/or coverage | Captured as core-v-docs issues
Code Coverage | Block/Statement Coverage | All Blocks covered | None allowed exception for those related to fixed parameters
| 100% Conditional Coverage | All conditions covered | Captured as core-v-verif issues
Functional Coverage | All cover-points attributed to a Vplan item | Human review | Captured as core-v-verif issues
| All cover properties attributed to a Vplan item | Human review | Captured as core-v-verif issues
| Cover-point coverage | 100% | Captured as core-v-verif issues
| Cover-property coverage | 100% | Captured as core-v-verif issues
Regression | Compliance Test Suite | All RISC-V Compliance tests run and passing | None allowed
| CORE-specific Test Suite | All tests run and passing | Captured as core-v-verif issues
Final Report | Verification Plans
Regression Results
Coverage Results
| Dependency overview | Used versions of software toolchain, simulator, ISS, etc. documented
| GitHub issue overview | No open (not explicitly waived) issues

## Software Requirements
Category | Item | Sign-off Criteria | Exceptions/Waivers